DISE | DELAYED IN-SITU SUSPENSION POLYMERIZATION

━━━━━━━━━━━━

# TIMELINE

# CAPABILITY

# AND COSTS

A focused laboratory programme to advance the integrated DISE platform from TRL 3 to TRL 4

| 6 months LABORATORY PROGRAMME | £50k–£75k INDICATIVE BUDGET | TRL 4 TARGET EXIT STATE |
| --- | --- | --- |

PROGRAMME INTENT

One formulation. One integrated evidence chain.

The programme is designed to identify and lock a candidate DISE formulation that meets the transport, timing, particle-formation and flow-preservation criteria together—not as isolated laboratory successes.

PROGRAMME DOSSIER  |  VERSION 1.0  |  SEPTEMBER 2026

Dr Juan Martin  •  Project Lead  •  University of East London

01 | EXECUTIVE DECISION BRIEF

# A six-month route to a defensible TRL 4

A bounded programme that converts the DISE architecture into repeatable laboratory evidence and a locked candidate formulation.

| TRL 3 CURRENT INTEGRATED MATURITY | 3 work blocks TWO MONTHS EACH | 6 exit gates GO / NO-GO DECISION |
| --- | --- | --- |

# The proposition

DISE can progress from TRL 3 to TRL 4 in approximately six months through a focused laboratory programme at the University of East London (UEL). The work converts the present analytical and experimentally testable architecture into an integrated laboratory demonstration, with quantified limits for transport, delayed activation, particle formation and preserved flow.

## What the programme will decide

Whether a complete DISE fluid can remain at or below 10 cP through the required transport simulation.

Whether delayed activation can be reproduced inside the 25–75 minute target window under defined thermal histories.

Whether curing remains intra-droplet, yielding discrete 70–600 µm particles rather than a connected bulk gel.

Whether the resulting particle assembly retains useful transport and permeability behaviour.

Whether one candidate formulation merits subsequent scale-up and relevant-environment validation.

INVESTMENT LOGIC

Fund the evidence chain, not a performance promise.

The £50,000–£75,000 range supports formulation screening, instrumentation, characterisation, bench-scale transport testing and disciplined down-selection. All numerical performance values remain qualification targets until measured.

02 | TIMELINE

# Three work blocks. Six months. One integrated decision.

Activities are sequenced so that expensive transport and permeability work begins only after the chemistry and timing envelope is credible.

| 01 | Formulation & induction window | MONTHS 1–2 |
| --- | --- | --- |

Establish candidate ratios around the fixed White Paper V5 chemistry and quantify thermal response, induction time, viscosity, droplet stability and pumpability.

OUTPUTS  Shortlist; thermal-dose model; viscosity map; stability screen; test methods

| 02 | Particle formation & transport | MONTHS 3–4 |
| --- | --- | --- |

Optimise particle morphology and size distribution, then test passage through representative packed-bed or porous-media systems.

OUTPUTS  Particle-size distributions; microscopy; agglomeration/fines data; transport response

| 03 | Repeatability & operating envelope | MONTHS 5–6 |
| --- | --- | --- |

Validate batch repeatability, pressure/permeability response and spatial distribution; lock the candidate formulation and define its safe operating envelope.

OUTPUTS  Locked formulation; SOP; operating envelope; risk register; TRL 4 evidence dossier

## Decision rhythm

Each block closes with a documented review: continue, reformulate, repeat a defined test, or stop. The next block is released only when its entry criteria are met. This protects budget, avoids confirmation bias and preserves traceability.

03 | WORK PROGRAMME

# What happens in each work block

A practical sequence built around measurements, reproducibility and explicit release criteria.

| PERIOD | PRIMARY QUESTION | CORE ACTIVITY | RELEASE EVIDENCE |
| --- | --- | --- | --- |
| M1–2 | Can the complete fluid be transported before activation? | Formulation screening; HP-DSC/thermal analysis; complete-fluid rheology; ageing; droplet stability; pumpability screen. | Candidate shortlist; repeatable induction response; ≤10 cP target assessed; no premature connected phase. |
| M3–4 | Can delayed conversion produce the right particles without fouling transport paths? | Particle synthesis; optical/SEM imaging; D10/D50/D90; circularity; agglomeration/fines; packed-bed or porous-media transport. | Discrete particles; 70–600 µm distribution target assessed; transport evidence; no connected bulk gel. |
| M5–6 | Is performance repeatable and bounded well enough to claim TRL 4? | Independent batches; pressure/permeability response; spatial distribution; sensitivity analysis; SOP and risk controls. | Repeatability package; operating envelope; locked formulation; scale-up recommendation. |

## Integrated test principle

NON-NEGOTIABLE

The same candidate must pass the combined criteria.

A formulation that meets viscosity but fails particle integrity—or produces strong particles but exceeds the transport viscosity limit—does not pass the programme. Isolated success cannot compensate for a failure elsewhere in the system.

04 | CAPABILITY

# A multidisciplinary delivery model

The programme combines formulation science with transport physics, particle characterisation and disciplined experimental design.

| CAPABILITY | ROLE IN DISE | REPRESENTATIVE OUTPUT |
| --- | --- | --- |
| Formulation & materials science | Design the reactive and continuous phases; control interfaces, compatibility and storage separation. | Candidate matrix and down-selection rationale |
| Polymerisation kinetics & thermal analysis | Translate time–temperature exposure into induction and cure behaviour. | Thermal-dose model and induction window |
| Rheology & pumpability | Measure the complete fluid under relevant shear, ageing and temperature conditions. | Viscosity envelope and hold/flush limits |
| Microscopy & particle analysis | Quantify morphology, size distribution, circularity, agglomeration and fines. | Image set and particle-quality dataset |
| Porous-media flow & pressure response | Assess passage, placement and retained flow using representative bench systems. | Pressure traces, distribution and permeability response |
| Experimental design & data analysis | Control variables, replication, uncertainty and decision rules. | Auditable evidence package and statistics |

## Delivery environment

UEL provides the multidisciplinary academic environment and laboratory base for the programme. Specialist analytical or high-pressure work may be commissioned externally where this improves technical quality, safety or value. Named personnel, facility time and external-provider scope should be confirmed at mobilisation.

05 | COSTS

# Indicative programme envelope

# £50,000 to £75,000

A transparent planning range aligned to the six-month TRL 3→4 scope. Final values depend on agreed test density, facility access and supplier quotations.

| £50k LEAN EVIDENCE PLAN | £62.5k PLANNING MIDPOINT | £75k ENHANCED TEST DENSITY |
| --- | --- | --- |

| COST CATEGORY | LOW | HIGH | WHAT IT ENABLES |
| --- | --- | --- | --- |
| Researcher & technical time | £20,000 | £30,000 | Experimental execution, supervision, data reduction and reporting |
| Materials & consumables | £8,000 | £12,000 | Monomers, crosslinkers, stabilisers, brines, disposables and safe handling |
| Laboratory & facility access | £6,000 | £9,000 | Rheology, thermal analysis, microscopy and controlled processing |
| Analytical characterisation | £6,000 | £10,000 | Particle sizing, imaging and specialist analytical tests |
| Test-rig fabrication & instrumentation | £5,000 | £8,000 | Representative transport/porous-media fixtures, sensors and modifications |
| Contingency & project control | £5,000 | £6,000 | Defined rework allowance, procurement variation and review gates |
| TOTAL | £50,000 | £75,000 | Six-month TRL 3→4 programme envelope |

Planning note: values are indicative, not quotations. VAT, institutional overhead treatment, procurement lead times and external-provider pricing must be confirmed in the agreed statement of work.

06 | TRL 4 EXIT CRITERIA

# What must be true at month six

TRL 4 is claimed only when the integrated laboratory evidence supports the critical functions and their interactions.

| 01 | TRANSPORT RHEOLOGY Complete-fluid viscosity is demonstrated at or below 10 cP across the agreed transport simulation. |
| --- | --- |
| 02 | DELAYED ACTIVATION A reproducible 25–75 minute induction window is measured under the defined thermal history. |
| 03 | DISCRETE FORMATION Conversion yields discrete particles with no connected bulk gel phase. |
| 04 | PARTICLE QUALITY The 70–600 µm target distribution is assessed with controlled agglomeration and fines. |
| 05 | FLOW EVIDENCE Bench transport, pressure response and permeability behaviour are documented. |
| 06 | CONTROL PACKAGE A locked formulation, operating envelope, SOP, risk register and scale-up plan are issued. |

## Evidence classification

Challenge requirements, DISE design targets and experimentally validated results must remain visibly separated in every report. Passing a gate means the agreed test method and acceptance rule have been met; it does not imply field qualification.

07 | GOVERNANCE & CONTROL

# Manage uncertainty before it becomes cost

A stage-gated structure contains technical risk and protects the programme from open-ended optimisation.

| CONTROL | PRACTICE | DECISION VALUE |
| --- | --- | --- |
| Pre-agreed acceptance criteria | Methods, replicates, tolerances and failure rules fixed before each test series. | Reduces retrospective interpretation |
| Fortnightly technical review | Review evidence, deviations, safety observations and budget-to-complete. | Enables timely correction or stop |
| Configuration control | Versioned formulation IDs and controlled changes to processing conditions. | Preserves traceability |
| Three-batch reproducibility | Independent preparation and testing of the down-selected candidate. | Tests repeatability, not one-off success |
| Specialist-test release gate | External HP/analytical work authorised only after bench entry criteria pass. | Protects the cost envelope |

## Principal uncertainties

Precursor concentration may conflict with the ≤10 cP transport ceiling.

Thermal history may activate the chemistry earlier than the nominal placement time.

Inter-droplet leakage or tack may create connected polymer or agglomerates.

High shear may shift droplet size outside the 70–600 µm window.

Particle integrity, fines or swelling may reduce retained flow under load.

08 | BEYOND THE SIX-MONTH SCOPE

# TRL 4 is the launch point for relevant-environment validation

The six-month dossier closes laboratory proof of concept. It does not include field deployment or a complete TRL 5 campaign.

NEXT-STAGE OBJECTIVE

Progress from a locked laboratory formulation to an integrated relevant-environment demonstration.

A subsequent programme should combine dynamic HPHT flow-loop circulation, in-situ transformation inside a representative fracture/coreholder and conductivity testing under closure stress.

## Illustrative next work package: months 7–9

Dynamic flow-loop circulation up to the defined 10,000 psi and 150°C challenge envelope, including pause/restart and line-fouling observations.

In-situ transformation within a fractured coreholder or representative fracture cell.

Particle-pack response at 4,500, 5,250 and 6,000 psi closure stress, including fines and deformation.

Measured permeability or conductivity retention, spatial distribution and micro-CT structural evidence where appropriate.

## Explicit exclusions from the £50,000–£75,000 envelope

Field trials, wellsite mobilisation or operator deployment.

Industrial manufacturing qualification and supply-chain scale-up.

A complete TRL 5 relevant-environment programme or certification campaign.

Unbounded formulation exploration outside the agreed White Paper V5 architecture.

## Recommended authorisation

Authorise the six-month programme subject to an agreed statement of work, named facilities and personnel, documented safety review, confirmed cost treatment and pre-approved gate criteria. Release later-stage expenditure only when the month-two and month-four evidence supports continuation.

09 | DOCUMENT CONTROL

# Programme basis and use

A concise planning document for technical review, laboratory scoping and funding discussion.

| DOCUMENT | DISE — Timeline, Capability & Costs |
| --- | --- |
| VERSION | 1.0 |
| DATE | September 2026 |
| PREPARED FOR | Technical review and programme scoping |
| PROGRAMME LEAD | Dr Juan Martin |
| INSTITUTIONAL CONTEXT | University of East London |
| CURRENT MATURITY | Integrated DISE platform: TRL 3, advancing toward TRL 4 |
| TECHNICAL BASIS | DISE Technical White Paper, Version 5.0 |

## Important qualification

DISE is an integrated TRL 3 technology architecture. The mechanisms and component technologies have supporting analytical and literature precedent, but the complete formulation has not yet demonstrated all challenge constraints simultaneously. Costs, timings and facility assumptions in this dossier are indicative and must be validated during mobilisation.

━━━━━━━━━━

STRUCTURAL REINFORCEMENT WITHOUT PERMANENT BLOCKAGE

DISE • Delayed In-Situ Suspension Polymerization